## 31 JULY (hidden)
Sn | ISSUES | STATUS | OWNER | Action Point | UPDATE
1 | MOBILE PAYMENT Payment through Control number MNO (TIGO) to Exim Bank. | Open | Exim ADC | Exim to complete with TIGO | Exim shared with TIGO expected customer journey. Waiting for Tigo response
2 | CONTRACT RENEWAL | Closed | Biz Logic/ Exim Ops | Current contract expired 31/03/2024 | Done
3 | MOBILE APP FOR PARENTS | Open | Exim ADC |  | Pending with Exim
4 | FORMAT FOR SUBSCRIPTION FEE CONTROL NUMBER Provide format of control number for subscription fee | Open | Biz Logic | Biz Logic to share with Exim Bank format of control number used for subscription fee payment to confirm if matches with current settings | Format already shared with Exim ADC, Exim ADC to provide feedback
5 | PARENT MOBILE APP SUBSCRIPTION FEE Biz Logic to enable subscription fee payment through MNOs | Open | Biz Logic | Biz Logic to share API | API shared with ADC Exim, Exim ADC to respond
6 | SET MOBILE APP SUBSCRIPTION PRICES Exim Bank to do research on subscription fee pricing | Closed | Exim Bank |  | Done, agreed to be 10,000 per annum
7 | WAKALA ENTRIES Commission, wrongly posting in CBS | Closed | Exim ADC |  | Done
8 | ACADEMIC YEAR FIELD User should be able to type academic year while entering data in the field of Academic Year instead of selecting from list | Open | Biz Logic | Start implementing in Jan 2024 | To be implemented in Second Phase, starting Jan 2024
9 | CONSOLIDATION REPORT Consolidation report-Details to be specified – Student details enquiry | Open | Biz Logic | To be implemented in Second Phase, 2024 | To be implemented in Second Phase, 2024
10 | HESLB LOANS How will system support records of student loans from HESLB | Open | Biz Logic | To be implemented in Second Phase, 2024 | To be implemented in Second Phase, 2024
11 | ALL REPORTS FOR BANK USER TO HAVE OPTION FOR SELECTING "ALL" | Closed | Biz Logic
12 | REPORT CALENDAR RANGE System Report Generation should allow date range | Open | Biz Logic |  | The following reports do not have calendar range: 1. Student Detail 2. Fee Details 3. Fee Balance
13 | PAYMENT FROM OTHER BANKS TO EXIM Payment using control number from other banks to Exim Bank. | Open | Exim ADC | Exim ADC to start implementation | Will be implemented after payment through MNOs completed
14 | OTHER TYPE OF PAYMENTS REQUIREMENT Biz Logic to extend the system to accommodate other sector apart from school payments (request received from other customers) | Open | Biz Logic |  | New requirement
15 | Registered University/College/School Report The report to show the status of the school for registered and deregistered | Open | Biz Logic |  | New requirement

## 26 AUG
Sn | ISSUES | STATUS | OWNER | Action Point | UPDATE
1 | MOBILE PAYMENT Payment through Control number MNO (TIGO) to Exim Bank. | Open | Exim ADC | Exim to complete with TIGO | User journey shared to Tigo for review,Next meeting to share the status.
2 | MOBILE APP FOR PARENTS | Open | Exim ADC |  | Separate meeting scheduled for alighment. Next meeting update will be shared.
3 | FORMAT FOR SUBSCRIPTION FEE CONTROL NUMBER Provide format of control number for subscription fee | Open | Biz Logic | Biz Logic to share with Exim Bank format of control number used for subscription fee payment to confirm if matches with current settings | Format already shared with Exim ADC, Exim ADC to provide feedback. Exim ADC to share the Update on next meeting.
4 | PARENT MOBILE APP SUBSCRIPTION FEE Biz Logic to enable subscription fee payment through MNOs. Parent can be abble to pay direct from Mobile App. | Open | Biz Logic | Biz Logic to share API | API shared with ADC Exim, Exim ADC to respond . ADC Team to respond
5 | ACADEMIC YEAR FIELD User should be able to type academic year while entering data in the field of Academic Year instead of selecting from list | Open | Biz Logic | Start implementing in Jan 2024 | To be implemented in Second Phase, starting Jan 2024. Still On UAT phase till 15th August 2024.
6 | CONSOLIDATION REPORT Consolidation report-Details to be specified – Student details enquiry | Open | Biz Logic | To be implemented in Second Phase, 2024 | To be implemented in Second Phase, 2024. Exim to share specific detail to be displayed.
7 | HESLB LOANS How will system support records of student loans from HESLB | Open | Biz Logic | To be implemented in Second Phase, 2024 | Biz Logic noted for Implimentation. And see how Will be accomodated in the system.
8 | REPORT CALENDAR RANGE System Report Generation should allow date range | Open | Biz Logic |  | The following reports do not have calendar range: 1. Student Detail 2. Fee Details 3. Fee Balance Biz logic will accommodate this by adding this Calendar Range as second option
9 | PAYMENT FROM OTHER BANKS TO EXIM Payment using control number from other banks to Exim Bank. | Open | Exim ADC | Exim ADC to start implementation | Will be implemented after payment through MNOs completed
10 | OTHER TYPE OF PAYMENTS REQUIREMENT Biz Logic to extend the system to accommodate other sector apart from school payments (request received from other customers) | Open | Biz Logic | New requirement | Demo can be demostrate on 15th Aug
11 | Registered University/College/School Report The report to show the status of the school for registered and deregistered | Open | Biz Logic | New requirement | Before the next meeting will be covered.
12 | VISA MASTER CARD PAYMENT Bank to check if Visa Mastercard can be used on fee payment | Open | Exim ADC | New requirement | ADC team to Discuss
13 | SYSTEM TO SUPPORT SCHOOL HOMEPACKAGE UPLOADING AND MARKING EXAM THROUGH SYSTEM Teacher can upload the homepackages and parent can view and student do it through Mobile app and return for marking the exam online. | Open | Biz Logic | New requirement | Biz logic will work on it and update
14 | AIRTEL TRACKER 1. UAT update 2. Airtel to update-onboarding school process | Open | Exim Br.Ops/ADC | New requirement | To be shared on next meeting.
15